## Gap Analysis
ID | Feature | Category | Effort | Impact | Phase | Dependencies | Status | Notes
GAP-1 | RSVP / "I'm Going" System | Event Engagement | M | *** | 2 |  | Not Started | Foundation feature — unlocks reminders, calendar depth, social proof, post-event prompts
GAP-2 | Pre-Event Reminders (1mo/1wk/1day) | Event Engagement | M | *** | 2 | GAP-1 | Not Started | Keeps users engaged between booking and attending
GAP-3 | Post-Event Rating Prompt | Event Engagement | S | ** | 1 | GAP-1 | Not Started | Closes the concert loop; drives concert history usage
GAP-4 | Calendar Sync (iCal/Google Calendar) | Event Engagement | S | *** | 1 |  | Not Started | Embeds app in daily life; ical-generator npm package exists
GAP-5 | RSVP Counts on Events | Event Engagement | S | * | 12 | GAP-1 | Not Started | Needs user scale to feel authentic
GAP-6 | On-Sale Date Alerts | Ticket Alerts | M | *** | 2 |  | Not Started | #1 fan pain point; Event model already has tickets.onSaleDate
GAP-7 | Presale Alerts | Ticket Alerts | M | *** | 2 |  | Not Started | Event model already has tickets.presales array
GAP-8 | Sold-Out Detection & Notifications | Ticket Alerts | M | ** | 4 |  | Not Started | Requires periodic status polling from TM/SeatGeek
GAP-9 | Waitlist for Sold-Out Events | Ticket Alerts | S | ** | 4 | GAP-8 | Not Started | Builds loyalty when tickets reappear
GAP-10 | Price Drop Alerts | Ticket Alerts | M | ** | 4 |  | Not Started | Notification model already has price_drop type defined
GAP-11 | Personalized Discovery Feed | Discovery | M | *** | 2 |  | Not Started | Cross-reference Last.fm similar artists with local events
GAP-12 | Trending Artists Chart | Discovery | M | * | 12 |  | Not Started | Needs user scale for meaningful data
GAP-13 | "Hot Shows" / Curated Picks | Discovery | S-M | ** | 11 |  | Not Started | Admin-curated works at any scale
GAP-14 | Festival Discovery & Lineup Tracking | Discovery | L | ** | 10 |  | Not Started | Seasonal (spring/summer) but high value
GAP-15 | Festival Set Times | Discovery | S | * | 12 | GAP-14 | Not Started | Narrow audience; depends on festival feature
GAP-16 | "Just Announced" Feed | Discovery | S | ** | 1 |  | Not Started | Events created in last 7 days for followed artists
GAP-17 | Similar Artist Auto-Follow Suggestions | Discovery | S | ** | 1 |  | Not Started | Uses existing Last.fm integration
GAP-18 | Music DNA Profile Visualization | Discovery | M | * | 11 |  | Not Started | Fun but one-time view; shareable
GAP-19 | Event Sharing / Open Graph Tags | Social | S-M | ** | 4 |  | Not Started | Rich previews when links shared on social media
GAP-20 | Share to Social Media Buttons | Social | S | ** | 1 |  | Not Started | One-click share to Twitter/X, Facebook, copy link
GAP-21 | "Request a Show" / Demand Tracking | Social | M | ** | 6 |  | Not Started | Engagement for non-touring artists
GAP-22 | Friend System / Social Connections | Social | L | ** | 9 |  | Not Started | Network effects; requires user scale
GAP-23 | Attendee List / "Who's Going" | Social | S-M | * | 12 | GAP-1 | Not Started | Needs user scale
GAP-24 | Web Push Notifications | Notifications | L | *** | 5 |  | Not Started | 2-5x better tap rate vs email; needs VAPID keys + service worker
GAP-25 | SMS Notifications (Twilio) | Notifications | M | ** | 5 |  | Not Started | 98% open rate; infrastructure exists (smsOptIn field)
GAP-26 | Multi-Location Notifications | Notifications | M | ** | 8 |  | Not Started | Home + work + travel destinations
GAP-27 | Configurable Notification Radius | Notifications | S | ** | 1 |  | Not Started | User model field + UI dropdown; instant personalization
GAP-28 | Notify for Any New Show (Global) | Notifications | S | ** | 1 |  | Not Started | Per-artist toggle to notify regardless of distance
GAP-29 | Granular Notification Preferences | Notifications | M | * | 11 |  | Not Started | Build when users complain about too many notifications
GAP-30 | Digest Frequency Options | Notifications | S-M | * | 11 |  | Not Started | Daily/weekly/real-time toggle
GAP-31 | Spotify Integration (Artist Import) | Integrations | L | *** | 5 |  | Not Started | Doubles music taste data; Spotify is dominant platform
GAP-32 | Apple Music Integration | Integrations | L | ** | 12 |  | Not Started | ~25% streaming market; complex auth
GAP-33 | Last.fm Scrobble Import | Integrations | S-M | * | 10 |  | Not Started | API already integrated; just extend to user.getTopArtists
GAP-34 | Shazam History Import | Integrations | L | * | 12 | GAP-32 | Not Started | No public API; indirect via Apple Music
GAP-35 | Artist Claim / Verification | Artist-Side | M | * | 12 |  | Not Started | Different product direction
GAP-36 | Artist Self-Service Event Management | Artist-Side | L | ** | 12 | GAP-35 | Not Started | Unlocks indie artist event coverage
GAP-37 | Artist Analytics Dashboard | Artist-Side | L | - | 12 | GAP-35 | Not Started | Artist-only; no fan impact
GAP-38 | Artist-to-Fan Posts / Messaging | Artist-Side | L | ** | 12 | GAP-35 | Not Started | Exclusive content; needs artist adoption
GAP-39 | Geo-Targeted Artist Posts | Artist-Side | M | * | 12 | GAP-38 | Not Started | Enhancement of artist posts
GAP-40 | Embeddable Event Widget | Distribution | M | * | 12 |  | Not Started | Growth tool; SEO/backlinks
GAP-41 | Artist "Track" Button Embed | Distribution | S | * | 12 |  | Not Started | User acquisition; needs artist adoption
GAP-42 | Venue Profiles | Venues | M | ** | 8 |  | In process | Aggregate existing event data into venue pages
GAP-43 | Venue Discovery / "Venues Near Me" | Venues | M | * | 11 |  | In process | Leaflet map of nearby venues
GAP-44 | Venue Following | Venues | M-L | ** | 8 |  | In process | Catches events that artist tracking misses
GAP-45 | Artist Extended Profiles / Bios | Content | M | * | 10 |  | Not Started | Last.fm provides bio/stats; fields exist but unpopulated
GAP-46 | Event Photos / User Content | Content | L | ** | 10 |  | Not Started | Concert scrapbook; needs S3/file upload
GAP-47 | Setlist Voting / Crowd-Sourced | Content | M | * | 12 |  | Not Started | Setlist.fm already covers most shows
GAP-48 | Live Concert Streaming | Content | XL | - | 12 |  | Not Recommended | Wrong scale; massive infrastructure investment
GAP-49 | Live Chat During Streams | Content | L | - | 12 | GAP-48 | Not Recommended | Depends on streaming which is not recommended
GAP-50 | Merch Integration (Shopify) | Commerce | S-L | * | 12 |  | Not Started | Start with simple links (S) before API (L)
GAP-51 | In-App Ticket Purchasing | Commerce | XL | ** | 12 |  | Not Started | Requires Ticketmaster business partnership
GAP-52 | Promoted Events / Paid Placement | Commerce | XL | - | 12 |  | Not Recommended | Needs significant traffic first
GAP-53 | Affiliate Revenue Dashboard | Commerce | M | - | 12 |  | Not Started | Internal admin tool only
GAP-54 | Progressive Web App (PWA) | Platform | M | *** | 5 |  | Not Started | manifest.json + service worker; 80% of native app value
GAP-55 | Mobile App (Native) | Platform | XL | ** | 12 |  | Not Started | PWA first; only if user base demands it
GAP-56 | Public API / Developer Access | Platform | L | - | 12 |  | Not Started | No unique data to expose yet
GAP-57 | Cross-Platform Distribution | Platform | XL | - | 12 |  | Not Started | Requires enterprise partnerships
GAP-58 | Onboarding Artist Import Flow | UX | M | *** | 2 |  | Not Started | Make-or-break for new user retention
GAP-59 | Configurable Search Radius | UX | S | ** | 1 |  | Not Started | Best effort-to-impact ratio on the list
GAP-60 | Multiple Saved Locations | UX | M | ** | 8 |  | Not Started | Home, work, vacation spots
GAP-61 | Dark Mode | UX | S-M | * | 11 |  | Not Started | Expected in modern apps
GAP-62 | Annual Recap / Year in Review | UX | M | ** | 5 |  | Not Started | Spotify Wrapped energy; massively shareable
GAP-63 | User Public Profile | UX | M | * | 9 | GAP-1 | Not Started | Needs active user content first
GAP-64 | Account Data Export (GDPR) | Compliance | S | * | 1 |  | Not Started | Trust signal; may become legally required
GAP-65 | Account Deletion Self-Service | Compliance | S | * | 1 |  | Not Started | GDPR/CCPA compliance

## Novel Features
ID | Feature | Category | Effort | Impact | Phase | Dependencies | Status | Notes
NEW-1 | Setlist Predictions | Predictive Intelligence | M | *** | 3 |  | Not Started | Analyze Setlist.fm song frequency; no competitor does this
NEW-2 | Tour Prediction / "Likely Coming" | Predictive Intelligence | M-L | ** | 7 |  | Not Started | Historical touring pattern analysis
NEW-3 | Ticket Price Intelligence | Predictive Intelligence | L | *** | 7 |  | Not Started | Google Flights for concerts; data moat deepens over time
NEW-4 | "You Missed This" FOMO Alerts | Predictive Intelligence | S-M | ** | 4 |  | Not Started | Post-event alert for unfollowed taste artists; use sparingly
NEW-5 | Live Concert Mode | At-the-Show | L | *** | 7 |  | Not Started | Real-time setlist tracking, ratings, check-in, photos
NEW-6 | Concert Time Machine / "On This Day" | At-the-Show | S | ** | 1 |  | Not Started | One query against concert history; massive emotional payoff
NEW-7 | Venue Intel / Crowd-Sourced Guide | At-the-Show | L | ** | 8 |  | Not Started | TripAdvisor for venues: sound, parking, tips, accessibility
NEW-8 | Post-Show Recap Card | At-the-Show | M | *** | 3 |  | Not Started | Auto-generated shareable card; Spotify Wrapped per concert
NEW-9 | Concert Buddy Matching | Social | L | ** | 9 |  | Not Started | Match solo concert-goers; solves "going alone" barrier
NEW-10 | Music Taste Compatibility Score | Social | M | ** | 9 |  | Not Started | Spotify Blend for concerts; drives friend invites
NEW-11 | Concert Challenges / Gamification | Social | M | ** | 6 |  | Not Started | Streaks, milestones, badges; motivates attendance + logging
NEW-12 | Concert Budget Tracker | Planning | M | ** | 10 |  | Not Started | Monthly/annual concert spending tracker with alerts
NEW-13 | "Surprise Me" Concert Finder | Planning | M | *** | 3 |  | Not Started | "Free Saturday, $50 budget" → constraint-based discovery
NEW-14 | Concert Road Trip Planner | Planning | L | ** | 10 |  | Not Started | Multi-city concert itineraries with drive times
NEW-15 | Opening Act Deep Dive | Planning | M | ** | 6 |  | Not Started | Preview openers with top songs and taste match
NEW-16 | Pre-Concert Hype Playlist | Planning | M | ** | 6 |  | Not Started | Auto-generate playlist 1 week before show
NEW-17 | Personal Concert Analytics Dashboard | Insights | M-L | ** | 7 |  | Not Started | Always-on stats + "concert personality" typing
NEW-18 | Smart Event Scoring (Match %) | Insights | M | *** | 3 |  | Not Started | Personal 1-100 match score per event; cuts through overload
NEW-19 | "Fans Also Attended" Recommendations | Insights | M-L | ** | 7 |  | Not Started | Collaborative filtering from concert history; needs scale
NEW-20 | Concert Weather Forecast | Logistics | S-M | ** | 6 |  | Not Started | Weather API for outdoor venues; people always Google this
NEW-21 | Smart Departure Time | Logistics | M | ** | 6 |  | Not Started | "Leave by 5:45 PM" with traffic + parking estimates
NEW-22 | Parking & Transit Guide | Logistics | M | * | 11 |  | Not Started | Crowd-sourced parking tips per venue
NEW-23 | Artist Milestone Tracking | Engagement | M | ** | 6 |  | Not Started | "Seen 5 times across 3 cities" — fan identity + pride
NEW-24 | Concert Countdown Widget | Engagement | S | ** | 1 |  | Not Started | Countdown to next show; builds anticipation
NEW-25 | "Deep Cuts" Alert | Engagement | S-M | ** | 4 |  | Not Started | Alert when artist plays rare song; unique to setlist platforms
NEW-26 | Concert Journal / Rich Notes | Engagement | M | ** | 6 |  | Not Started | Structured prompts turn history into personal archive
NEW-27 | Calendar Gap Recommendations | Engagement | M | *** | 3 | GAP-1 | Not Started | "Nothing planned for March — here are 5 matches"
NEW-28 | Structured Concert Reviews | Community | M | ** | 9 |  | Not Started | Sound, energy, value ratings; verified attendance
NEW-29 | "Ask a Fan" Community Q&A | Community | L | * | 12 |  | Not Started | Needs active user base for timely answers
NEW-30 | Crowd-Sourced Artist Live Rating | Community | S | ** | 1 |  | Not Started | Aggregate existing ratings; answers "Are they good live?"